## Taul1
General deadlines 2023 | Note | Deadline (yyyy-mm-dd) | Action/deadline | Responsibility
Week 03 | At least 30 working days before Expert Group | 2023-01-20 | Delivery of major update proposals for NordDRG (via NordDRG Forum) from the national organizations. All changes must contain the technical changes. | National organisations Nordic Casemix Centre
Week 08 | At least 10 working days before Expert Group meeting | 2023-02-23 | Delivery of minor update proposals for NordDRG (via NordDRG Forum) from the national organizations. All the changes must contain the technical changes | National organisations Nordic Casemix Centre
Week 10 |  | 2023-03-9-10 (Thursday-Friday) | Expert Group MEETING regarding recommended updates | Nordic Casemix Centre National organisations
Week 12 | 5 working days after Expert Group meeting | 2023-03-20 | Delivery of Files of technical changes to Nordic Casemix Centre | National organisations report to Nordic Casemix Centre
Week 13 | 15 working days after Expert Group meeting | 2023-03-31 | Report of Expert Group Meeting results: List of accepted, rejected and postponed proposals Files of technical changes | Nordic Casemix Centre reports to Expert Group and Board
Week 14 | 17-20 working days after Expert Group meeting | 2023-04-07 | BOARD MEETING on update decisions with the technical changes | Board
Week 14-15 |  |  | Easter | Easter
Week 18 | 20 working days after Board meeting | 2023-05-05 | Delivery of Combined version definition tables (Excel) and National version grouping definitions (PL0) to national organisations (JSON, csv, Excel files) (via NordDRG Forum) | Nordic Casemix Centre
Week 21 | 10 working days after delivery of definition tables | 2023-05-22 | Comments and corrections to National version grouping definitions (PL0) | National organisations report to Nordic Casemix Centre
Updated definition tables will be redelivered if needed. National organisations may comment the delivered material.
Week 23 | 10 working days after the delivery of PL0 | 2023-06-06 | Publication of Combined version definition tables (Excel) and National version grouping definitions (PL1) (JSON, csv, Excel files) (via NordDRG Forum) | Nordic Casemix Centre
Week 31 |  | 2023-08-04 | Delivery of National ICD and NCSP versions to Nordic Centre | National organisations
Week 34 | 15 working days after delivery of national versions | 2023-08-25 | NCSP+ and ICD10+ update by Nordic Centre and the delivery of the national organisations for comments | Nordic Casemix Centre
Week 36 |  | 2023-09-04 | Expert Group MEETING to complete NCSP+ and ICD10+ and check properties of new codes. Comments and corrections to NCSP+ and ICD10+ mapping | Nordic Casemix Centre National organisations
The Excel version of NCSP+ and ICD+ table includes a date when each code is taken in use in each national version (use_ice, use_fin etc). The national organisations responsibility is to check that all national changes are included and that the new codes are mapped to a corresponding NCSP+ and ICD+code (which may be new or old). If no comments are received before the deadline, the mapping in NCSP+ is considered valid for further work. The Excel version includes filters which makes finding of the changed codes easier. (Filter for example for use_fin=2009-01-01 or just use_fin=2009 [in Excel 2007])
Week 39 | 15 working days after Expert Group meeting | 2023-09-29 | Delivery of Combined version definition tables (Excel) and National version grouping definitions (PR0) to national organisations (JSON, csv, Excel files) (via NordDRG Forum) | Nordic Casemix Centre
Week 41 | 10 working days after delivery of definition tables | 2023-10-13 | Comments and corrections to National version grouping definitions (PR0) | National organisations report to Nordic Casemix Centre
Updated definition tables will be redelivered if needed. National organisations may comment the delivered material.
Week 43 | 10 working days after the delivery of PR0 | 2023-10-27 | Publication of Combined version definition tables (Excel) and National version grouping definitions (PR1) (JSON, csv, Excel files) (via NordDRG Forum) | Nordic Casemix Centre